## Weekly Ellie
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Project Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 9 | 9 | 0 | 0 - get familiarized with course 0 - catch up on missed meeting and project decisions 5 - connect with all members 5 - draft management plan Objectives 0 - complete lab 1 7 - make project video | 3.5 |  |  |  |  | 4 |  | 1.5 | 1. Write sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 video presentation | 1. had an exam and class to finish week one, got a late start to the class as a result. | 1. I have brought myself up to date on the project and finished the previous class | Iron out requirements and roles design database | 12
2 | 05/17-05/23 | 9 | 8 | 1 | 2- database design 3- write sql code for table creation 5- team meeting 0- quiz 0- learning | 2.5 |  | 3 | 2.5 |  | 1 |  |  | 1. SQL code for create tabes | 1. had a friend with some health problems and I spent a fair amount of time with them at the ER | 1. They're doing better and going back home out of state for the weekend- plan to move forward with less distraction | meet with team and continue SQL implementations | 10
3 | 05/24-05/30 | 9.5 | 8.5 | 1 | 5- team meeting 2- Data Quality planning 3- begin implementation of data quality measures 0- learning 5- Database design section of SDD 5- SPPP related work and management overview | 2.5 |  | 1.5 | 2.5 |  | 3 |  |  | 1. SQL code- procedures file 2. sections of SPPP 3. section of SDD | 1. Some debugging needs to be done in my stored procedures- something is causing an error to be thrown in testing on my local machine | 1. It's certainly a solvable problem, just one I havent been able to dedicate time to yet, which is the plan in the next iteration. Once that issue is sorted, configuring the database in the cloud and ingesting the data, probably through use of a python script, is the plan. | Once that issue is sorted, configuring the database in the cloud and ingesting the data, probably through use of a python script, is the plan, and then exploring database security | 11

## Weekly Eric
Your Lead Roles: QA Manager
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 5/10-5/16 | 13 | 12 | 1 | 0 - Learn github desktop (Lab 1), Learn about risk mangement, read project documents and watched videos, learn about TensorFlow and nueral networks, studied other CS673 projects 4 - Wrote testing plan in SPPP 5 - Organized and facilitated first meeting and communications to make sure we are were on the same page | 8 |  |  |  | 2 | 2 |  |  | 1. Wrote testing section of SPPP 2. Wrote meeting minutes from 5/14 3. Committed bio to github (Lab 1) | 1. I have not worked with neural networks in the past so I need to learn about that 2. Some team members got a late start due to finals overlapping this week 3. I haven't done front-end coding in the past so I will have to study that in order to be ready for testing | 1. I'm working on studying these tools. 2. We seem like we are back on track now as of Saturday. We will see how well we are able to collaborate on and complete Iteration 0 3. I will work on studying these tools. | 1. I will work on studying these tools more. 2. Plan for next week depends on how the next few days go. 3. I will work on studying these tools more. | 10
2 | 5/17-5/24 | 17 | 16 | 1 | 0. Read a lot about machine learning and tensor flow. Studied other CS673 projects. 3/4. Created control model for testing neural network 5. Document control model and discuss with team. | 5 |  |  | 5 | 5 | 1 |  |  | 1. Wrote control model testing code, class diagram, and conceptual reserach doucments and committed to github
3 | 5/24-5/31 | 9 | 8 | 1 | 0. Reviewed project testing principles and studied other projects 4. Tested SQL server 5. Wrote SQL server test and control model into STD 7. Created video for iteration 1 about control model | 3 |  |  |  | 1 | 2 |  | 2 | 1. Wrote SQL server test and control model into STD

## Weekly Alex
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7.5 | 6.5 | 1 | 0 - read about django, angular, docker, how to package it all together 5 - communicate with team, determine what times we can all meet at 6 - set up git, create lab1 branch w/ template, create branch protection rule, PR template, project, issues testing 7 - research similar products | 3 |  |  |  |  | 0.5 | 2.5 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit to team.md 3. Set up GitHub Project, Issues, other Git configurations | 1. Not familar with Django framework, how it will work with Angular and Docker. Testing out package and deployment process needed. 2. Team communication is not great | 1. Create simple hello world app with django, angular, package it up and deploy 2. Continue to actively chat in discord to make sure team is on the same page | 0 - continue to learn Django 7 - research best cloud provider to host 4 - implement a basic hello world on Django and deploy | 9
2 | 05/17-05/23 | 18 | 17 | 1 | 0 - continued to read about django, angular, docker, how to package it all together 3 - create ci/cd pipeline to automate the build and deploy to web server process, skeleton angular app, skeleton django app 6 - create aws account, set up server, enable branch protection rules in github, configure security scans (codeQL), create Docker Service Account | 3 |  |  | 12 |  |  | 2 |  | 1. Edit SPPP section 2. merge PR containing Angular skeleton code, CI/CD code 3. Configure AWS, Docker, Git | 1. Tasks took longer than anticipated, a lot of learning, planning, trial and error. 2. free tier web server may not have enough resources to run appication - we will see. | 1. I have learned a lot through the trial and error - direction forward is more clear. 2. If needed, can bump up ec2 instance type to allocate more resources (RAM, CPUs) | 3 - start to work on integrating django backend with angular frontend 4 - test django and angular integration 6 - adjust server settings in AWS | 14
3 | 05/24-05/30 | 8 | 7 | 1 | 0 - learned about docker build with cache to speed up process 3 - modifying package and deploy script to docker build from cache 6 - create AWS RDS PostgreSQL Database, share credentials and endpoint details with team 7 - SDD, STD, SPPP (updates) Presentation video | 0.5 |  |  | 1 |  |  | 2 | 3.5 | 1. Video presentation 2. SDD, STD, SPP (updates) | 1. Busy week at work, wasn't able to play with code as much. Made up for it last week with contributions | 1. Work on next coding steps next week | 3 - start to work on integrating django backend with angular frontend 4 - test django and angular integration 6 - adjust server settings in AWS | 14

## Weekly Rui
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
2 | 05/17-05/23 | 12 | 11 | 1 | 0 - watch class recordings 1 - add user stories and acceptance tests to the ice cube of pivotal tracker 2 - design the basic neural network model and the evaluation algorithm for the recommender model 5 - team meeting 7 - finish lab 2 and quiz 1 | 3 | 2 | 4 |  |  | 1 |  | 2 |  | 1. cannot setup the connection to the AWS rds instance. 2. cannot store the dataset to the db. | 1. complete the backend code to insert dataset to the db. 2. write backend code to extract data from the db. | 1. complete the pyodbc program. 2. train the recommender system model | 10
3 | 05/24-05/30 |  | 15 | 1 | 0 - read lecture slides and study recommendation system algorithms 1 - add risk management categories 2 - create the backend services to load the pre-trained neural network model, to save user preference data, and to get unwatched movies of the user 5 - team meeting 7 - finish parts of the SDD | 5 | 1 | 5 |  |  | 1 |  | 3 | 1. Write 3 sections of SDD and add a class diagram and flow flow chart for the neural network model 2. Update the Requirements, Design and Implementation categories of the SPPP 3. Develop backend services for the project. | 1. not familiar with Django framework. Hard to get the user input data from the frontend. 2. Need to develop hybrid recommendation system for the new user case. | 1. Study Django and item-based hybrid recommendation algorithm | 1. Complete the prediction method and save user preference method. 2. Create a prototype of hybrid recommendation model. | 10

## Weekly Sujeet
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Risk Management Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 12 | 11 | 1 | 0 - learn git and Risk management 1 - define high level requirements, 5 - Make Risk Mangement plan and updated team 6 - set up git 7 - Discussion with teams | 4.5 | 0.5 |  |  |  | 6 | 0.5 | 0.5 | 1. Write 1 sections of SPPP 2. Set up git, commit a test message on git 3. Updated Risk Management Sheet | 1. not familar with tensor flow framework, hard to write any code on it. 2. I am not much familiar with CSS to completely own angular work. | Updated team leader about the issue to plan efficiently | - continue to work on risk mitigation - continue to define requirements - Continue to discuss with team to distribute task efficiently | 8

## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Any other metrics defined in your SPPP
0 | 5/10-5/16 | 5 - Met and coordinated group roles 2 - decided on project idea 1 - SPPP Requirements, Testing, management plan objectives, risk assessment, configuration plan, testing plan 7 - Create initial project video |  | This iteration was mainly for planning and coordination, which we have done. We're in a good place moving into Iteration 1 and the beginning of development. | Much greater presence and communication, along with more meetings, should improve our process | 0 |  |  |  |  | 31 | 30 | 1 | 19 | 0.5 | 0 | 0 | 2 | 14.5 | 0.5 | 2
1 | 5/17-5/30 | Set up the configuration of our repo and web app, performed interrogation on the data and initial NN recommendation model |  |  |  | 1 | 3 |  |  |  | ~69.5 | ~67.5 | 2 | ~20 | 0 | ~6.5 | ~23 | ~6 | ~8 | ~4 | ~10
2
3
~ indicates estimation when data was not provided by a team member in time

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments