## Weekly Ellie
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Project Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 9 | 9 | 0 | 0 - get familiarized with course 0 - catch up on missed meeting and project decisions 5 - connect with all members 5 - draft management plan Objectives 0 - complete lab 1 7 - make project video | 3.5 |  |  |  |  | 4 |  | 1.5 | 1. Write sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 video presentation | 1. had an exam and class to finish week one, got a late start to the class as a result. | 1. I have brought myself up to date on the project and finished the previous class | Iron out requirements and roles design database | 12

## Weekly Eric
Your Lead Roles: QA Manager
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 5/10-5/16 | 13 | 12 | 1 | 0 - Learn github desktop (Lab 1), Learn about risk mangement, read project documents and watched videos, learn about TensorFlow and nueral networks, studied other CS673 projects 4 - Wrote testing plan in SPPP 5 - Organized and facilitated first meeting and communications to make sure we are were on the same page | 8 |  |  |  | 2 | 2 |  |  | 1. Wrote testing section of SPPP 2. Wrote meeting minutes from 5/14 3. Committed bio to github (Lab 1) | 1. I have not worked with neural networks in the past so I need to learn about that 2. Some team members got a late start due to finals overlapping this week 3. I haven't done front-end coding in the past so I will have to study that in order to be ready for testing | 1. I'm working on studying these tools. 2. We seem like we are back on track now as of Saturday. We will see how well we are able to collaborate on and complete Iteration 0 3. I will work on studying these tools. | 1. I will work on studying these tools more. 2. Plan for next week depends on how the next few days go. 3. I will work on studying these tools more. | 10

## Weekly Alex
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7.5 | 6.5 | 1 | 0 - read about django, angular, docker, how to package it all together 5 - communicate with team, determine what times we can all meet at 6 - set up git, create lab1 branch w/ template, create branch protection rule, PR template, project, issues testing 7 - research similar products | 3 |  |  |  |  | 0.5 | 2.5 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit to team.md 3. Set up GitHub Project, Issues, other Git configurations | 1. Not familar with Django framework, how it will work with Angular and Docker. Testing out package and deployment process needed. 2. Team communication is not great | 1. Create simple hello world app with django, angular, package it up and deploy 2. Continue to actively chat in discord to make sure team is on the same page | 0 - continue to learn Django 7 - research best cloud provider to host 4 - implement a basic hello world on Django and deploy | 9

## Weekly Rui
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Weekly Sujeet
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Risk Management Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 12 | 11 | 1 | 0 - learn git and Risk management 1 - define high level requirements, 5 - Make Risk Mangement plan and updated team 6 - set up git 7 - Discussion with teams | 4.5 | 0.5 |  |  |  | 6 | 0.5 | 0.5 | 1. Write 1 sections of SPPP 2. Set up git, commit a test message on git 3. Updated Risk Management Sheet | 1. not familar with tensor flow framework, hard to write any code on it. 2. I am not much familiar with CSS to completely own angular work. | Updated team leader about the issue to plan efficiently | - continue to work on risk mitigation - continue to define requirements - Continue to discuss with team to distribute task efficiently | 8

## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Any other metrics defined in your SPPP
0 | 5/10-5/16 | 5 - Met and coordinated group roles 2 - decided on project idea 1 - SPPP Requirements, Testing, management plan objectives, risk assessment, configuration plan, testing plan 7 - Create initial project video |  | This iteration was mainly for planning and coordination, which we have done. We're in a good place moving into Iteration 1 and the beginning of development. | Much greater presence and communication, along with more meetings, should improve our process | 0 |  |  |  |  | 31 | 30 | 1 | 19 | 0.5 | 0 | 0 | 2 | 14.5 | 0.5 | 2
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments