## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 2022-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
add new team members
Lack of motivation or responsibility
Communication | duplicate work | Muliple team member working on same task | 2 | 3 | 3 | 4*3*3=36 | team leader and all team member | 2022-06-21 | Review User Stories and make sure to have clear and well defined requirements | No user stories created yet. | Open
worked on wrong components
useless work
inconsistent work
Requirements | unclear requirements
scope creep
constant requirements changes
Management | improper task assignments
| improper planning | Iteration not planned well | 2 | 4 | 4 | 4*2*4=32 | All Team member | 2022-06-21 | Have a retrospective meeting at the end of each iteration and improve | To be planned and the end of the iteration. | Open
| lack of management skills | unclear expectation | 2 | 4 | 3 | 4*2*3=24 | All Team member | 2022-06-21 | set clear expectation | No user stories created yet | Open
Technology competence | Not familiar with the framework used | Team member not familiar with the framework choosen for development | 4 | 4 | 4 | 2*2*4=16 | All Team member | 2022-05-31 | select a framework which most of the team members are familiar with | Tensor Flow and Angular choosen | Open
| Not familiar with the programming language used | Team member not familiar with the programming languages choosen for development | 4 | 4 | 4 | 2*2*4=16 | All Team member | 2022-05-31 | select a programming language which most of the team members are familiar with | Python, TypeScript, CSS choosen | Open
| Not familiar with unit testing | Team member not familiar with unit testing | 2 | 4 | 4 | 4*2*4=32 | All Team member | 2022-05-31 | Focus on unit tesing from begining | Development not started | Open
Other technology incompetence
Not familiar with Git
Design and implementation | Improper design
improper technology stack
| Messy code | unorganised/ unstructured code written by team members | 3 | 2 | 3 | 3*4*3=36 | Design/Implementation Leader and All Team member | 2022-06-21 | peer review to avoid messy code | Development not started | Open
Testing | Not enough testing | insufficient testing | 2 | 4 | 4 | 4*2*4=32 | QA Leader and All team | 2022-06-21 | make sure to have enough test cases to cover all scenarios including edge cases | Development not started | Open
Integration and deployment | Not enough time for integration and deployment | Not having enough time to integrate or deploy code | 3 | 2 | 3 | 3*4*3=36 | Configuration Leader and All team | 2022-06-21 | set up CI/CD pipeline to avoid last minute rush | Development not started | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.